BOARD OF INVESTMENT OF SRI LANKA

# Investment Proposal

Establishment of a Photovoltaic Solar Module Assembly Facility in Sri Lanka

US$ 15 million foreign direct investment | 250 direct jobs by Year 3 | 350 MW annual capacity

Illustrative / training-use proposal - company particulars, projections and transaction assumptions are fictional.

Applicant at a glance HelioVolt Asia Manufacturing (Pvt) Ltd., a proposed Sri Lankan subsidiary of HelioVolt Energy Systems GmbH (Germany), seeks BOI facilitation for an export-oriented solar module assembly plant. The project is designed as a three-year scale-up and targets more than 80% of output for export, subject to BOI eligibility confirmation.

| Proposal item | Applicant position |
| --- | --- |
| Applicant | HelioVolt Asia Manufacturing (Pvt) Ltd. (proposed) |
| Project | PV solar module assembly: cell interconnection, lamination, framing, junction-box installation, testing and packing |
| Investment | US$ 15.0 million total project envelope |
| Employment | 250 direct full-time jobs by the end of Year 3 |
| Target capacity | 75 MW in Year 1; 200 MW in Year 2; 350 MW in Year 3 |
| Export orientation | Target >80% of output for export; indicative Year 3 export sales US$ 52 million |
| Preferred site | Horana EPZ, with Mirijjawila as the alternative location |

# 1. Executive Summary

HelioVolt Energy Systems GmbH proposes to establish a Sri Lankan manufacturing subsidiary, HelioVolt Asia Manufacturing (Pvt) Ltd., to assemble photovoltaic solar modules for regional and international export markets. The project combines imported high-efficiency solar cells and selected components with local assembly, testing, packaging, logistics and selected ancillary sourcing.

Decision requested from BOI We request BOI to evaluate the project for approval under the applicable investment regime; advise the applicant on the appropriate concession package; identify a suitable industrial plot; coordinate the principal regulatory interfaces; and confirm the customs, tax, land and utility arrangements that can be made available under prevailing law and BOI policy.

## 1.1 Investment case

• Foreign direct investment commitment: US$ 15.0 million over three years.

• Direct employment: 250 positions by Month 36, with a focus on engineering, mechatronics, quality, operations, supply chain and EHS roles.

• Export manufacturing: more than 80% of production intended for foreign markets, supporting the project’s positioning as an export-oriented manufacturing investment.

• Industrial footprint: approximately 10 acres requested, subject to BOI site planning and the final plant layout.

• Output ramp: 75 MW in Year 1, 200 MW in Year 2 and 350 MW in Year 3.

• Strategic contribution: technology transfer, skilled employment, higher-value manufacturing and foreign-exchange-generating exports.

## 1.2 Assessment-ready proposal structure

The submission has been structured so that each material request is traceable to a stated project fact, an evidence item, an approval dependency, a proposed milestone or a measurable project KPI. This format is intended to reduce ambiguity during BOI appraisal and to make the proposal machine-readable for future digital or AI-assisted assessment workflows.

# 2. Applicant and Sponsor Profile

| Proposal item | Applicant position |
| --- | --- |
| Sri Lankan entity | HelioVolt Asia Manufacturing (Pvt) Ltd. (proposed private limited company) |
| Registered office | Level 18, East Tower, World Trade Center, Colombo 01 (assumed address for illustration) |
| Shareholder | HelioVolt Energy Systems GmbH, Germany - 100% proposed foreign ownership, subject to applicable Sri Lankan law and approvals |
| Proposed paid-in capital | US$ 7.5 million |
| Planned shareholder / project funding | US$ 15.0 million total project funding envelope, including equity and approved project finance |
| Business activity | Manufacture/assembly and export of photovoltaic solar modules and related assemblies |
| Sponsor experience | Illustrative European PV equipment and energy-systems group with assumed operations in module assembly, industrial automation and energy-project supply chains |

## 2.1 Governance and local capability

• Managing Director: Lukas Weber (assumed for this illustrative case).

• Chief Operating Officer / Plant Director: Anushka Perera (assumed).

• Head of Finance & Administration: Daniel Schmitt (assumed).

• The company will establish local accounting, HR, EHS, procurement and compliance functions and maintain BOI reporting and record-keeping requirements.

# 3. Proposed Project and Manufacturing Scope

The proposed plant will perform solar module assembly rather than upstream polysilicon, ingot or wafer manufacturing. Core processes will include cell tabbing/stringing, lay-up, EVA encapsulation, vacuum lamination, framing, junction-box installation, EL inspection, flash testing, high-voltage testing, labeling and export packing.

| Project parameter | Proposed value | Assessment basis |
| --- | --- | --- |
| Plant type | PV module assembly and testing facility | Export-oriented manufacturing project |
| Project implementation | 36 months | Three-stage ramp-up |
| Land requirement | ~10 acres | Subject to detailed layout and BOI site availability |
| Factory gross floor area | ~160,000 sq. ft. | Illustrative master-planning assumption |
| Initial product | N-type / TOPCon compatible glass-backsheet and glass-glass modules | Product mix to be finalized with OEM technology provider |
| Installed line capacity | 350 MW/year at full scale | Target Year 3 output |
| Grid requirement | Up to ~4 MVA contracted demand at full scale | Illustrative planning requirement; final load study to be submitted |
| Rooftop solar | 1.5 MWp planned, subject to grid and regulatory approvals | Energy cost and resilience measure |
| Export share | >80% of output targeted | To support export-manufacturing positioning |

## 3.1 Capital expenditure and funding use

| Use of funds | US$ million | What it covers |
| --- | --- | --- |
| Land and civil works | 4.5 | Lease premium / site preparation, factory building, utilities and production fit-out |
| Assembly automation | 5.0 | Tabber-stringers, laminators, framing, testing and material handling systems |
| Environmental / energy infrastructure | 1.0 | ETP, VOC extraction, waste storage and planned 1.5 MWp rooftop solar |
| Working capital and bonded inventory | 3.5 | Cells, glass, frames, EVA, backsheets, junction boxes and operating liquidity |
| Training and operational setup | 1.0 | Recruitment, technical training, commissioning and compliance setup |
| Total | 15.0 | Three-year project envelope |

# 4. Location, Land and Logistics Request

The company seeks a site in an industrial zone capable of supporting containerized inbound materials, reliable medium-voltage electricity, worker access and future expansion. BOI’s published zone directory confirms current BOI contacts for Horana EPZ and Mirijjawila EPZ, among other zones. The final site decision should be based on current plot availability, lease terms, utility capacity, environmental suitability and logistics performance rather than a fixed assumption about price or availability. (R3)

| Criterion | Horana EPZ - preferred | Mirijjawila - alternative |
| --- | --- | --- |
| Strategic rationale | Closer to established western industrial cluster and Colombo logistics corridor | Strong southern logistics position and access to Hambantota port corridor |
| Land need | ~10 acres contiguous plot requested | ~10 acres contiguous plot requested |
| Expansion | Adequate for planned facility; expansion subject to plot availability | Potentially attractive where larger contiguous land parcels are available |
| Workforce | Priority access to western-region technical and operator labour market | Recruitment and training plan required for the initial workforce ramp |
| BOI action requested | Confirm available plots, current lease and service charges, utility headroom and site-readiness | Confirm available plots, lease terms, utilities and site-readiness |

Land allocation request Please provide current BOI availability, lease / reservation terms, service charges, plot dimensions, access roads, water and electricity capacity, and any environmental or zoning constraints for the preferred and alternative sites. No fixed land price is assumed until BOI issues a current site-specific quotation.

# 5. BOI Approval, Incentives and Policy Stability

The applicant requests BOI assessment for the most suitable approval route under the BOI Law and the investment-incentive framework applicable at the time of approval. The project is designed around export-oriented manufacturing and a material foreign investment commitment. Current BOI investment-incentive material describes customs/PAL concessions for specified categories of BOI projects and provides enhanced capital allowances for qualifying new investments, while the precise package depends on the approved project structure and applicable thresholds. (R1)

| Requested area | Applicant request | Confirmation requested from BOI |
| --- | --- | --- |
| BOI project approval | Approval of the proposed export-oriented PV module assembly project under the appropriate BOI mechanism. | Applicable section / agreement route, qualifying conditions and agreement process. |
| Customs / project imports | Concessionary treatment for eligible capital goods, plant, machinery, construction items and export-oriented raw materials, as permitted under the applicable BOI/customs regime. | Eligible HS codes, documentation, approval path and any bank guarantee / monitoring conditions. |
| Tax / capital allowance | Access to all incentives available to a qualifying US$15m export-manufacturing project, including any enhanced capital allowance treatment. | Current CIT treatment, ECA eligibility and loss-utilization rules for this project. |
| Foreign exchange / repatriation | Ability to fund the project from foreign sources and remit profits/capital in accordance with prevailing exchange-control law and BOI agreement terms. | Exact account, remittance and reporting requirements applicable to the project. |
| Investor / expatriate services | Facilitation for key foreign technical specialists required for installation and commissioning. | Required documentation and visa/residency process. |
| Policy stability | Clarity on the contractual and statutory protections applicable to the approved project. | Form and duration of any BOI agreement protections, together with change-in-law treatment. |

Important investor position HelioVolt is not asking BOI to accept a pre-stated tax or customs outcome as a fact. The company requests a formal confirmation of the incentive package available to this project under the law and policy in force when the application is approved. This reduces later rework and gives the investment committee an auditable approval basis.

# 6. Approval and Implementation Timeline

The applicant proposes a 12-month pre-commercial implementation target, followed by a 24-month production ramp to reach full Year 3 capacity. The proposed regulatory sequence is an applicant planning assumption; BOI and other authorities will determine statutory processing times and dependencies.

| Phase | Timing target | Key actions | Primary dependency |
| --- | --- | --- | --- |
| 1. Incorporation & application | Weeks 1-3 | Company incorporation, project information pack, BOI application, financial capacity evidence | BOI application completeness |
| 2. Site & environmental screening | Weeks 3-8 | Site reservation, preliminary engineering, environmental screening / submissions | Site availability and environmental pathway |
| 3. Agreement & lease | Weeks 8-12 | Finalize BOI agreement, land lease and project conditions | Negotiation and required approvals |
| 4. Design & construction | Months 3-9 | Detailed design, building approvals, civil works, utilities and equipment procurement | Engineering approvals and import permissions |
| 5. Commissioning & compliance | Months 9-12 | Install machinery, trial runs, EHS controls, inspections, operating approvals | Successful inspections / licensing |
| 6. Production ramp | Months 13-36 | Scale 75 MW → 200 MW → 350 MW, recruit 250 staff, deepen exports | Customer qualification and working capital |

# 7. Customs, Import-Export and Market Access

The company expects a high share of imported production inputs during the initial operating period, including solar cells, solar glass, EVA encapsulant, backsheets, aluminum profiles, junction boxes and selected electrical components. Sri Lanka Customs confirms that its Industries & Services Directorate administers economic procedures that include bonded warehousing, export-oriented manufacturing schemes and coordination with BOI. The Export Facilitation Unit handles applications for customs duty relief for export-oriented manufacturing under TIEP and related schemes, including raw materials and capital goods. (R4)

| Customs workflow | Applicant process | Control point for assessment |
| --- | --- | --- |
| Import registration / approved bill of materials | Submit project equipment and raw-material lists against the approved project scope. | Reconcile item description, HS classification, quantities and project eligibility. |
| Capital goods | Seek applicable concession / TIEP or BOI facility before shipment where required. | Confirm approval reference before cargo arrival. |
| Raw materials | Use appropriate export-oriented / bonded procedure for eligible inputs. | Track inputs, production yield, finished goods and export clearances. |
| Bonded storage | Use approved bonded warehouse arrangements where appropriate. | Maintain inventory controls and customs security conditions. |
| Export clearance | Ship finished modules with full commercial and technical documentation. | Match export declaration, invoice, packing list, COO and customer documentation. |
| Local sales | Treat any domestic release strictly under the applicable BOI/customs approvals and tax treatment. | Pre-clear the quantity and fiscal impact of any local sale. |

Customs support requested Please nominate the BOI / Customs coordination path and provide the current checklist for capital machinery, raw materials, bonded storage, green-channel or other facilitation programs available to an approved export-manufacturing project.

# 8. Electricity, Energy Cost and Resilience

Power quality and energy-cost predictability are material investment considerations because lamination, material handling, testing and factory utilities require stable electrical supply. PUCSL’s current industrial tariff page classifies I-2 supplies as 400/230V with contract demand above 42 kVA and I-3 supplies as 11 kV and above. The published I-3 schedule currently shows time-of-use charges of LKR 10.25/kWh (day), LKR 23.50/kWh (peak) and LKR 5.90/kWh (off-peak), plus a fixed charge and maximum-demand charge. These rates are subject to tariff decisions and revisions. (R6, R7)

| Energy issue | Project response | BOI / utility request |
| --- | --- | --- |
| High daytime consumption | Schedule energy-intensive processes during lower-cost daytime / shoulder periods where manufacturing quality permits. | Confirm feasible connection category, available capacity and connection lead time. |
| Demand charges | Design plant for high load factor and power-factor correction; monitor maximum demand. | Confirm medium-voltage connection and substation requirements. |
| Tariff volatility | Model base / downside electricity-cost scenarios and review tariff exposure annually. | Provide current industrial tariff reference and any applicable BOI / utility support programs. |
| Resilience | Install 1.5 MWp rooftop solar and backup systems for critical controls and safety loads. | Confirm grid-interconnection and rooftop PV approval pathway. |
| Power quality | Use UPS / power-conditioning for sensitive automation and test equipment. | Confirm service standard and metering requirements. |

# 9. Environmental, Health and Safety Management

The facility will be designed around a preventive EHS approach. The applicant anticipates environmental review for wastewater, air emissions/VOCs, scheduled waste, noise, occupational safety and construction impacts. BOI and the Central Environmental Authority will determine the applicable environmental approval and licensing pathway based on the final site, process description and regulatory classification.

| Risk area | Potential source | Proposed control | Evidence / approval |
| --- | --- | --- | --- |
| Wastewater | Glass washing, cleaning and process residues | Collection, segregation, treatment and reuse; no uncontrolled discharge | Design basis; environmental approval / license as applicable |
| VOC / air emissions | Lamination and curing processes | Local exhaust ventilation, filtration and preventive maintenance | Air-emission design and monitoring plan |
| Scheduled waste | Damaged cells, solder dross, contaminated containers | Bunded storage, manifests and licensed disposal / recovery route | Waste register and contracts / licenses |
| Noise | Framing, material handling and production equipment | Equipment isolation, acoustic controls and worker hearing protection | Noise survey / occupational controls |
| Electrical safety | High-voltage testing and automated equipment | Interlocks, isolation, arc-flash controls, permits and trained operators | EHS procedures and commissioning records |

# 10. Employment, Skills and Technology Transfer

| Year | Direct employment | Output target | Indicative export sales |
| --- | --- | --- | --- |
| Year 1 | 80 | 75 MW | US$ 12 million |
| Year 2 | 180 | 200 MW | US$ 30 million |
| Year 3 | 250 | 350 MW | US$ 52 million |

The company will prioritize local recruitment for operators, technicians, quality inspectors, warehouse staff, maintenance personnel, administrative roles and a growing proportion of engineering functions. A structured training program will be established with local technical institutes and universities, supplemented by sponsor-led training in production quality, automation, electrical safety and EHS.

# 11. Commercial Model and Export Plan

The plant will source high-efficiency solar cells and critical components from qualified international suppliers and assemble finished modules in Sri Lanka. Target customers will include regional EPC contractors, utility-scale project developers, distributors and renewable-energy integrators.

• Primary target markets: India, Pakistan, East Africa, selected Middle East markets and EU / UK buyers subject to product standards and rules of origin.

• Year 3 sales target: approximately US$ 52 million, driven by 350 MW annual output and a product mix weighted toward higher-efficiency modules.

• Commercial qualification: IEC-certified product family, customer factory audits, bankable quality documentation and traceable bill-of-materials controls.

• Market-access strategy: use Sri Lanka’s trade-agreement and preferential-access framework only where the product satisfies applicable rules of origin and other qualification requirements. The BOI’s current investment guide notes preferential access arrangements involving India and Pakistan, and other schemes such as the UK DCTS, EU GSP schemes, APTA and SAFTA. (R2)

# 12. Key Risks and Mitigation Commitments

| Risk | Potential impact | Mitigation / commitment | BOI support requested |
| --- | --- | --- | --- |
| Land availability | Project delay or higher upfront cost | Maintain two-site shortlist; finalize only after written site/lease confirmation | Current plot availability and lease terms |
| Tariff / energy volatility | Operating-cost variability | TOU scheduling, 1.5 MWp rooftop PV, demand management and annual scenario review | Utility connection and tariff guidance |
| Customs classification / approvals | Cargo delay and working-capital pressure | Pre-clear BOM, HS codes and approval references; use BOI/Customs coordination | Current customs checklist and named contact |
| Environmental approval timing | Construction / commissioning delay | Submit process description and environmental control design early | Confirm applicable environmental pathway |
| Policy uncertainty | Investor risk perception | Use formal BOI agreement / approval documentation and maintain compliance reporting | Explain contractual and statutory protection available |
| Skilled labour ramp | Production quality or throughput constraints | Recruitment pipeline, training academy and expatriate technical support during start-up | Workforce / visa facilitation guidance |
| Export demand | Under-utilized capacity | Stage investment and customer qualification before full ramp | General export facilitation / market intelligence support |

# 13. Specific Requests to the Board of Investment

1. Accept this proposal for preliminary assessment and advise the appropriate investment approval route.

2. Confirm whether the proposed activity and export profile qualify for the available BOI incentive framework and specify the applicable conditions.

3. Provide a shortlist of currently available plots in Horana EPZ and Mirijjawila (or equivalent industrial locations) meeting approximately 10 acres, with land, service, utility and environmental information.

4. Coordinate or direct the applicant to the relevant process for CEB / utility connection, environmental clearances and building approvals.

5. Provide the current customs facilitation process for project capital goods, raw materials, bonded warehousing and export manufacturing.

6. Advise the expected approval sequence, principal submission documents and indicative agency interfaces so that the applicant can build a bankable implementation schedule.

7. Confirm the conditions, duration and compliance obligations attached to any BOI agreement or concession package offered to the project.

# 14. Appraisal Data Sheet for BOI / AI Assessment

The following compact data sheet is intended to make the case suitable for structured assessment. Each row can be mapped to a decision field, evidence request, risk flag or scoring rule in an AI-assisted workflow.

| Assessment field | Value | Evidence expected | Status |
| --- | --- | --- | --- |
| Foreign investment | US$ 15.0m | Sponsor funding letter / bank evidence / board resolution | Applicant commitment |
| Direct jobs by Year 3 | 250 | Workforce plan and payroll assumptions | Target |
| Export share | >80% output | Sales plan, customer pipeline and BOM/export model | Target / eligibility-sensitive |
| Year 3 capacity | 350 MW/year | Equipment quotations and line specification | Target |
| Land requirement | ~10 acres | Preliminary site layout | Requested |
| Preferred location | Horana EPZ | BOI site shortlist / availability letter | Requested |
| Alternative location | Mirijjawila | BOI site shortlist / availability letter | Requested |
| Grid requirement | Up to ~4 MVA | Electrical load study | Planning assumption |
| Rooftop PV | 1.5 MWp | Engineering concept and grid-interconnection plan | Planned |
| Environmental pathway | To be confirmed | Process description and site-specific screening | Open item |
| Customs pathway | BOI + Customs economic procedures / TIEP / bonded route as applicable | Approved BOM, HS codes, facility approvals | Open item |
| Tax / incentive package | To be confirmed by BOI | Current incentive schedule and project agreement | Open item |
| Implementation target | 12 months to commercial start; 36 months to full ramp | Integrated project schedule | Applicant target |

# 15. Annexes and Supporting Information

## Annex A - Indicative three-year implementation milestones

| Milestone | Target month | Deliverable / gating event |
| --- | --- | --- |
| Incorporation complete | 1 | Sri Lankan project company established |
| BOI application accepted | 2 | Application pack complete and logged |
| Site identified / reserved | 2-3 | Plot and utility data confirmed |
| BOI agreement / lease | 3 | Project agreement and site documentation executed |
| Detailed design complete | 5 | Issued-for-construction package |
| Civil works substantially complete | 8 | Factory, utilities and EHS infrastructure ready |
| Equipment installed | 10 | Production line mechanically and electrically complete |
| Trial production | 11 | Quality validation / customer samples |
| Commercial launch | 12 | Operational approvals and first commercial shipment |
| 200 MW run-rate | 24 | Year 2 target achieved |
| 350 MW run-rate | 36 | Full-scale target achieved |

## Annex B - Illustrative evidence register

| Evidence ID | Document / record | Purpose in assessment |
| --- | --- | --- |
| EV-01 | Sponsor corporate profile and ownership chart | Confirms investor identity, ultimate ownership and governance |
| EV-02 | Audited financial statements / funding evidence | Tests financial capacity for the US$15m commitment |
| EV-03 | Preliminary plant layout and land plan | Tests land requirement and engineering feasibility |
| EV-04 | Equipment quotations and vendor list | Tests CAPEX reasonableness and installed capacity |
| EV-05 | Three-year staffing plan | Tests 250-job commitment and capability development |
| EV-06 | Export sales strategy / customer pipeline | Tests export share and revenue assumptions |
| EV-07 | Environmental process note | Tests licensing pathway and mitigation design |
| EV-08 | Electrical load study | Tests power demand, tariff category and connection scope |
| EV-09 | BOM and HS-code schedule | Tests customs treatment and import-control requirements |
| EV-10 | Integrated project schedule | Tests implementation realism and approval dependencies |

# 16. Reference Base

The following sources were used to shape the illustrative proposal. Current regulatory outcomes should be confirmed directly with BOI, Sri Lanka Customs, PUCSL, CEB and other competent authorities before any real application is submitted.

| Ref. | Source | Use | Link / note |
| --- | --- | --- | --- |
| R1 | Board of Investment of Sri Lanka, Investment Incentives - 2025 (official BOI publication). | Current reference for enhanced capital allowances and customs/PAL/VAT incentive structures. | https://investsrilanka.com/wp-content/uploads/2025/09/Investment-incentives-23.09.2025.pdf |
| R2 | Board of Investment of Sri Lanka, Investment Guide - 2025 (official BOI publication). | Reference for investment climate, market access and BOI framework. | https://investsrilanka.com/wp-content/uploads/2025/01/BOI-Investment-Guide-01.01.2025.pdf |
| R3 | Board of Investment of Sri Lanka, BOI Zone / Park Contact Directory. | Reference for current zone contacts, including Horana EPZ and Mirijjawila EPZ. | https://investsrilanka.com/home/contact-boi-sri-lanka/ |
| R4 | Sri Lanka Customs, Industries & Services Directorate. | Reference for economic customs procedures, bonded warehousing, TIEP and BOI coordination. | https://www.customs.gov.lk/about-us/directorates-and-divisions/industries-services-directorate/ |
| R5 | Sri Lanka Customs, Customs BOI Coordination Directorate. | Reference for BOI cargo screening and coordination functions. | https://www.customs.gov.lk/about-us/directorates-and-divisions/customs-boi-coordination-directorate/ |
| R6 | PUCSL, Industrial Electricity Tariff. | Reference for current industrial tariff categories and I-3 time-of-use rates. | https://www.pucsl.gov.lk/electricity/tariff/industrial/ |
| R7 | PUCSL, End User Tariff Decisions. | Reference for the current tariff-decision cycle and revisions. | https://www.pucsl.gov.lk/end-user-tariff-decisions/ |
| R8 | Applicant reference pack supplied for this illustrative case. | Contains the original project assumptions, location comparison, operational, EHS and financial concepts that informed this draft. | User-provided reference document |

# 17. Declaration and Signature

For and on behalf of HelioVolt Asia Manufacturing (Pvt) Ltd. (proposed)

| Name | Title | Signature / date |
| --- | --- | --- |
| Lukas Weber | Managing Director | ____________________________ / 19 August 2026 |
| Anushka Perera | Proposed Plant Director, Sri Lanka | ____________________________ / 19 August 2026 |

Applicant declaration The information and projections in this illustrative proposal are prepared for planning and assessment demonstration. Any actual submission would be supported by documentary evidence, final engineering, financial commitments, current regulatory requirements and site-specific studies, and would remain subject to BOI and other statutory approvals.